| COMPUTING IMPACT PLAN 2024 - 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Priority 2 |  |  | - Embed the new progressive and sequenced KAPOW curriculum (foundation subjects) consistently within all year groups, with a key focus on ensuring pupils know more, remember more, and can apply more to their year group end points. |  |  |  |  |  |  |  |  |  |  |  |
| Lead person accountable for the plan: J. Carr Governor/s responsible for the plan: Gemma Smith |  |  |  |  | Finance Plan: £114 bid put in September 2024 |  |  |  |  | Account Code: T.B.C. |  |  |  |  |
| Success Criteria & Milestones |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Success Criteria: End of year impact - |  |  |  |  |  | Autumn Target |  | Spring Target |  |  |  |  | Summer Target |  |
| 1. | Subject leaders develop an increasingly secure knowledge of their curriculum area, across all year groups and how it is delivered through KAPOW |  |  |  |  | 50% |  | 75% |  |  |  |  | 100% |  |
| 2. | Teachers can demonstrate an increasingly secure knowledge and understanding of their year group’s curriculum. |  |  |  |  | 50% |  | 75% |  |  |  |  | 100% |  |
| 3. | Disadvantaged pupils, including pupils with SEND, will have equity in provision and opportunity to enable them to succeed to be in line with their peers. |  |  |  |  | 50% |  | 75% |  |  |  |  | 100% |  |
| 4. | Ensure all teachers consistently offer appropriate challenge, support, and aspiration across all subjects for all pupils. |  |  |  |  | 50% |  | 75% |  |  |  |  | 100% |  |
| 5. | Ensure all children achieve lesson objectives in the lesson- no matter the subject or are supported to do so through catch-up provision (Catch up, keep up). |  |  |  |  | 50% |  | 75% |  |  |  |  | 90% |  |
| 6. | All teaching is judged as ‘at least good’ with minimal learning time wasted or disrupted. |  |  |  |  | 50% |  | 75% |  |  |  |  | 100% |  |
| Monitoring (explicitly against success criteria/ milestones- see annual monitoring plan for specific detail) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who Staff member responsible |  | What |  |  |  |  | When – How regularly will you conduct monitoring activities? |  | Where- Where will you review/report the outcomes of the monitoring activities? |  |  | External Validation- How will you gain external validation of your work (eg School Improvement Partner, Governors etc) |  |  |
| J. Carr |  | Learning walks- Observations of teaching- Work scrutiny- Learning environment checks- Planning/ assessment checks- Subject leader action plans - PM meetings - Pupil Voice discussions - Parental views - Staff views |  |  |  |  | Weekly / Termly /Annually |  | Staff meetings SLT meetings |  |  | Leadership Team – termly Rose Review - annually |  |  |
| Actions (required to achieve Success Criteria) |  |  |  |  |  |  | Lead person responsible |  | Timescale- start/end |  | Training/ CPD needs |  |  | Resources/cost/time |
| Key driver 1-Subject leaders develop an increasingly secure knowledge of their curriculum area, across all year groups and how it is delivered through KAPOW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1a) The Computing Lead is to download the Long-Term Plan for Computing, from the KAPOW website. This is to be saved electronically in the following folder: Planning> Planning Support > Kapow > Computing > Long Term Plan. A paper copy is to be filed in the Subject Leaders folder for Computing, located in the Meeting Room cupboard. A PDF version is to be uploaded to the school website, for the wider community to view. |  |  |  |  |  |  | J. Carr |  | Sept 24 |  | - |  |  | Non-directed time |
| 1b) The Computing Lead is to download the Progression of Skills and Knowledge document, from the KAPOW website. This is to be saved electronically in the following folder: Planning> Planning Support > Kapow > Computing > Progression of Knowledge and Skills. A paper copy is to be filed in the Subject Leaders folder for Computing, located in the Meeting Room cupboard. A PDF version is to be uploaded to the school website, for the wider community to view. |  |  |  |  |  |  | J. Carr |  | Sept 24 |  | - |  |  | Non-directed time |
| 1c) The Computing Lead is to download the National Curriculum Coverage document, for Computing, from the KAPOW website. This is to be saved electronically in the following folder: Planning> Planning Support > Kapow > Computing > Progression of Knowledge and Skills. A paper copy is to be filed in the Subject Leaders folder for Computing, located in the Meeting Room cupboard. A PDF version is to be uploaded to the school website, for the wider community to view. |  |  |  |  |  |  | J. Carr |  | Sept 24 |  | - |  |  | Non-directed time |
| 1d) The Computing Lead is to create a Spiral Learning document, for Computing. This will show prior learning for the unit and the next steps (this is different to the Long-Term Plan, as consecutive units do not always build upon one another). This is to be saved electronically in the following folder: Planning> Planning Support > Kapow > Computing > Spiral Learning Sequence. A paper copy is to be filed in the Subject Leaders folder for Computing, located in the Meeting Room cupboard. A PDF version is to be uploaded to the school website, for the wider community to view. |  |  |  |  |  |  | J. Carr |  | Sept 24 |  | - |  |  | Non-directed time |
| Key driver 2- Teachers can demonstrate an increasingly secure knowledge and understanding of their year group’s curriculum. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2a) Liaise with SLT (following A Day in The Life visits and the Rose Review visit) to discuss their Learning Walk findings. |  |  |  |  |  |  | J. Carr J. Allington (SLT responsible for Teaching and Learning) |  | Dec 24 Apr 25 Jul 25 |  | - |  |  | Non-directed time |
| Key driver 3- Disadvantaged pupils, including pupils with SEND, will have equity in provision and opportunity to enable them to succeed to be in line with their peers. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3a) Computing Lead to discuss with class teachers about ‘disadvantaged pupils’ and cross refer it to data held on OTrack, to ensure that they are being given learning tasks in line with their academic potential. |  |  |  |  |  |  | J. Carr G. Smith |  | Dec 24 Apr 25 Jul 25 |  | - |  |  | Non-directed time |
| 3b) Computing Lead to discuss with class teachers about SEND pupils and ensure that Adaptive Teaching is taking place. Kapow offers suggestion about how to accomplish this in each of their lesson plans. |  |  |  |  |  |  | J. Carr G. Smith |  | Dec 24 Apr 25 Jul 25 |  | - |  |  | Non-directed time |
| 3c) Computing Lead to seek additional enrichment opportunities for those classed as Disadvantaged. |  |  |  |  |  |  | J. Carr J.Allington (Enrichment Lead) |  | Nov 24 Feb 25 May 25 |  |  |  |  | Non-directed time |
| Key driver 4 - Ensure all teachers consistently offer appropriate challenge, support, and aspiration across all subjects for all pupils. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4a) Set expected outcomes – targets for Computing on OTrack should be aspirational. |  |  |  |  |  |  | Class Teachers |  | Nov 24 Feb 25 May 25 |  | - |  |  | Non-directed time |
| 4b) Through discussions with teachers, ensure that Adaptive Teaching for Computing is taking place. Kapow offers suggestion about how to accomplish this in each of their lesson plans: Pupils Needing Extra Support / Pupils Working at Greater Depth. |  |  |  |  |  |  | J. Carr G. Smith |  | Dec 24 Apr 25 Jul 25 |  | - |  |  | Non-directed time |
| Key driver 5 - Ensure all children achieve lesson objectives in the lesson- no matter the subject or are supported to do so through catch-up provision (Catch up, keep up). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5a) Conference pupils regularly to ensure they can recall the Key Knowledge for Computing and make links with their learning. During Pupil Voice, the Computing Lead is to highlight, in pink, the facts that the children can recall. This is then to be copied immediately and handed back to the teaching team, to show where the knowledge gaps exist. The original copy is to be filed in the in the Subject Leaders folder for Computing, located in the Meeting Room cupboard. |  |  |  |  |  |  | J. Carr |  | Dec 24 Apr 25 Jul 25 |  | - |  |  | Non-directed time |
| Key driver 6 - All teaching is judged as ‘at least good’ with minimal learning time wasted or disrupted. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6a) Computing Lead to liaise with SLT, following the termly A Day in The Life visits to each year group, to identify teachers who would benefit from PPA support/ coaching/ CDP for Computing. |  |  |  |  |  |  | J. Carr J. Allington (SLT responsible for Teaching and Learning) |  | Dec 24 Apr 25 Jul 25 |  | PPA support/ coaching/ CDP for Computing. |  |  | Non-directed time |
| 6b) Staff to carryout Teacher Knowledge Audit for Computing, to identify teachers who would benefit from PPA support/ coaching/ CDP. |  |  |  |  |  |  | Class Teachers |  | Jul 25 |  | PPA support/ coaching/ CDP for Computing. |  |  | INSET |
| Autumn Term Summary Evaluation of Impact (refer to Success Criteria & Milestones only) |  |  |  | Key Driver 1: 1a) Completed 09/24 1b) Completed 09/24 1c) Completed 09/24 1d) Completed 09/24 Key Driver 2: 2a) 2b) 2c) Key Driver 3: 3a) 3b) 3c) Key Driver 4: 4a) 4b) Key Driver 5: 5a) 5b) 5c) Key Driver 6: 6a) 6b) |  |  |  |  |  |  |  |  |  |  |
| Spring Term Summary Evaluation of Impact (refer to Success Criteria & Milestones only) |  |  |  | Key Driver 1: 1a) 1b) 1c) 1d) Key Driver 2: 2a) 2b) 2c) Key Driver 3: 3a) 3b) 3c) Key Driver 4: 4a) 4b) Key Driver 5: 5a) 5b) 5c) Key Driver 6: 6a) 6b) |  |  |  |  |  |  |  |  |  |  |
| Summer Term Summary Evaluation of Impact (refer to Success Criteria & Milestones only) |  |  |  | Key Driver 1: 1a) 1b) 1c) 1d) Key Driver 2: 2a) 2b) 2c) Key Driver 3: 3a) 3b) 3c) Key Driver 4: 4a) 4b) Key Driver 5: 5a) 5b) 5c) Key Driver 6: 6a) 6b) |  |  |  |  |  |  |  |  |  |  |
| To do: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |